## Team
Initials | First | Last | Email | GitHub Username
CX | Chenyang | Xu | cxu30@stevens.edu | KyrieXu-bot
HZ | Hongzhi | Zhao | hzhao38@stevens.edu | oberonbot
FJ | Fan | Jia | fjia5@stevens.edu | Schwarzwald5987
|  |  | GitHub Repository: | https://github.com/KyrieXu-bot/ScrumProject

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2021-10-03 | 24 |  | 0
2021-10-18 | 18 | 6 | 250 | 100 | 150
2021-11-07 | 12 | 6 | 150 | 90 | 180
2021-11-15 | 6 | 6 | 180 | 100 | 160
2021-12-02 | 0 | 6 | 200 | 120 | 180

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | CX | Done
1 | US02 | Birth before marriage | HZ | Done
1 | US03 | Birth before death | HZ | Done
1 | US04 | Marriage before divorce | CX | Done
1 | US05 | Marriage before death | FJ | Done
1 | US06 | Divorce before death | FJ | Done
2 | US07 | Less than 150 years old | HZ | Done
2 | US08 | Birth before marriage of parents | FJ | Done
2 | US09 | Birth before death of parents | HZ | Done
2 | US10 | Marriage after 14 | FJ | Done
2 | US11 | No bigamy | CX | Done
2 | US12 | Parents not too old | CX | Done
3 | US13 | Siblings spacing | CX | Done
3 | US14 | Multiple births <= 5 | FJ | Done
3 | US15 | Fewer than 15 siblings | HZ | Done
3 | US23 | Unique name and birth date | HZ | Done
3 | US22 | Unique IDs | CX | Done
3 | US29 | List deceased | FJ | Done
4 | US30 | List living married | CX | Done
4 | US31 | List living single | FJ | Done
4 | US35 | List recent births | HZ | Done
4 | US36 | List recent deaths | HZ | Done
4 | US27 | Include individual ages | FJ | Done
4 | US33 | List orphans | CX | Done

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2021-10-03 | 24 |  | 0
Sprint 1 | 2021-10-18 | 18 | 6 | 250 | 100 | 150
Sprint 2 | 2021-11-06 | 12 | 6 | 150 | 90 | 180
Sprint 3 | 2021-11-15 | 6 | 6 | 180 | 100 | 160
Sprint 4 | 2021-12-02 | 0 | 6 | 200 | 120 | 180

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Birth before death | HZ | Done | 150 | 60 | 200 | 80 | 2021-06-24
T03.01 | Store birth date | HZ | Done | 10 | 30
T03.02 | Store death date | HZ | Done | 10 | 30
T03.03 | Compare birth and death dates | HZ | Done | 10 | 30
US05 | Marriage before death | FJ | Done | 200 | 120 | 150 | 45
T05.01 | Find marriage record for individual | FJ | Done | 10 | 30
T05.02 | Find marriage date | FJ | Done | 10 | 30
T05.03 | Compare marriage date to birth date | FJ | Done | 10 | 30
US01 | Dates before current date | CX | Done | 100 | 50 | 160 | 60
T01.01 | Store birth date | CX | Done | 10 | 30
T01.02 | Store marriage date | CX | Done | 10 | 30
T01.03 | Store divorced date | CX | Done | 10 | 30
T01.04 | Store death date | CX | Done | 10 | 30
T01.05 | Compare these dates with current system date | CX | Done | 10 | 30
US02 | Birth before marriage | HZ | Done | 150 | 60 | 100 | 40
T02.01 | Store birth date for individual | HZ | Done | 10 | 30
T02.02 | Find marriage date | HZ | Done | 10 | 30
T02.03 | Compare birth date with marriage date | HZ | Done | 10 | 30
US04 | Marriage before divorce | CX | Done | 150 | 80 | 100 | 30
T04.01 | Store marriage date | CX | Done | 10 | 30
T04.02 | Find divorce date for the family | CX | Done | 10 | 30
T04.03 | Compare the marriage date and divorce date | CX | Done | 10 | 30
US06 | Divorce before death | FJ | Done | 150 | 80 | 100 | 50
T06.01 | Find divorce date for individual | FJ | Done | 10 | 30
T06.02 | Store death date | FJ | Done | 10 | 30
T06.03 | Compare individual with | FJ | Done | 10 | 30
Review Results
Keep integration and refactoring
modify the acceptance tests as well as comments
The output of dates needs to be ordered correctly
Keep doing:
join Zoom meeting this Friday
update gedcom codes
Avoid:
Balance the workload of each team member, and the amount of code for each developer is as consistent as possible
Commit codes on Github too randomly, we should commit frequently

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Less than 150 years old | HZ | Done | 200 | 120 | 160 | 100 | 2021-12-24
T07.01 | Store death date | HZ | Done
T07.02 | Store birth date | HZ | Done
T07.03 | Compare 150 with lifetime length | HZ | Done
US08 | Birth before marriage of parents | FJ | Done | 160 | 80 | 160 | 80
T08.01 | Store birth date of children | FJ | Done
T08.02 | Store marriage date of parents | FJ | Done
T08.03 | Compare the birth and marriage date | FJ | Done
US09 | Birth before death of parents | HZ | Done | 180 | 100 | 120 | 110
T09.01 | Store birth date of children | HZ | Done
T09.02 | Store death date of parents | HZ | Done
T09.03 | Compare the birth date and death date | HZ | Done
US10 | Marriage after 14 | FJ | Done | 140 | 70 | 100 | 50
T10.01 | Store birth date | FJ | Done
T10.02 | Store marriage date | FJ | Done
T10.03 | Calculate the marriage year and compare it with 14 | FJ | Done
US11 | No bigamy | CX | Done | 180 | 120 | 250 | 160
T11.01 | Store divorce date | CX | Done
T11.02 | Store the marriage date of the people with divorce | CX | Done
T11.03 | Test if the marriage date exists | CX | Done
US12 | Parents not too old | CX | Done | 200 | 160 | 150 | 120
T12.01 | Store birth date of children | CX | Done
T12.02 | Store birth date of mother and father | CX | Done
T12.03 | Subtract both dates and compare: 1)60 with mother; 2) 80 with father | CX | Done
Review Results
Keep integration and refactoring
Complete the acceptance tests as well as comments
We did a great job, the coding velocity is faster than the last sprint. Keep enhancing, everyone!
Keep doing:
join Zoom meeting this Monday
'No bigamy' user stories can be refactored, the logic might be a bit complex, which is not good for the future iteration.
Avoid:
Balance the workload of each team member, and the amount of code for each developer is as consistent as possible
Be careful about the committed version on GitHub, it happened to be overwritten. Take care next time.

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 | Siblings spacing | CX | Done | 160 | 100 | 180 | 120 | 2021-11-15
T13.01 | Store Siblings' birth dates |  | Done
T13.02 | Compare any of two dates by subtracting them |  | Done
T13.03 | Judge if the subtraction is larger than 8 months or less than 2 days |  | Done
US14 | Multiple births <= 5 | FJ | Done | 150 | 100 | 160 | 100
T14.01 | Store the children's birth dates of each family |  | Done
T14.02 | Test if the dates are the same |  | Done
T14.03 | Test if the number of dates larger than 5 given the same-date condition |  | Done
US15 | Fewer than 15 siblings | HZ | Done | 120 | 80 | 100 | 80
T15.01 | Store the children's information for each family |  | Done
T15.02 | Check if the number of children fewer than 15 |  | Done
US23 | Unique name and birth date | HZ | Done | 140 | 60 | 180 | 90
T23.01 | Store one's name |  | Done
T23.02 | Store one's birth date |  | Done
T23.03 | Compare both information with others' |  | Done
US22 | Unique IDs | CX | Done | 120 | 80 | 100 | 70
T22.01 | Store everyone's IDs |  | Done
T22.02 | Compare with each other and find if there is duplication |  | Done
US29 | List deceased | FJ | Done | 100 | 50 | 120 | 50
T29.01 | Store the death date |  | Done
T29.02 | Print and list all the people that have death date |  | Done
Review Results
About the 'multiple birth' story, the result is available for this Gedcom file
Good work overall, the coding velocity is faster. We finished all stories of Sprint 3 in 10 days! Last Sprint, everyone!
The iteration of Sprint 2 did a lot of help to Sprint 3. Nice job, Hongzhi.
Keep doing:
join Zoom meeting this Monday and Thursday
About 'multiple birth' story, Add a situation: considering the birth on the same day
Modify the acceptance tests as well as comments
If convenient, we can still use Wechat to share some small changes of codes
Avoid:
Try to take every possible condition into consideration, and testing condition should also be more complex.
Still be careful about the committed version on GitHub

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US30 | List living married | CX | Done | 140 | 75 | 140 | 60 | 2021-12-02
T30.01 | Store married wives and husbands
T30.02 | Check if wives have deseased date
US31 | List living single | FJ | Done | 140 | 75 | 150 | 60
T31.01 | Store individuals married date
T31.02 | Check if individuals have married date
T31.03 | Check if individuals have deseased date
US35 | List recent births | HZ | Done | 120 | 90 | 150 | 90
T35.01 | Store all individuals' birth dates
T35.02 | Store the current date time
T35.03 | Check if the birth dates is 30 days later than current time
US36 | List recent deaths | HZ | Done | 120 | 90 | 150 | 90
T36.01 | Store all individuals' death dates
T36.02 | Store the current date time
T36.03 | Check if the death dates is 30 days later than current time
US27 | Include individual ages | FJ | Done | 140 | 80 | 120 | 80
T27.01 | Store individuals' birth dates
T27.02 | Store individuals' death dates
T27.03 | Store the current date time
T27.04 | Check if some individuals are dead
T27.05 | Subtract the current date with birth dates to calculate the age
US33 | List orphans | CX | Done | 200 | 160 | 180 | 140
T33.01 | Store children's birth dates
T33.02 | Store children's parents' death date
T33.03 | Check if children is younger than 18
T33.04 | Check if children's parents' are both dead
Review Results
Congratulations, folks! We finished all sprints. Yes!
Good work overall, there is no problem with everyone's contributions. Nice work.
Keep doing:
join Zoom meeting this Monday and Thursday
Make preparations for the last retrospective meeting
Check for every comment for the codes
If convenient, we can still use Wechat to share some small changes of codes
Avoid:
Get rid of some unnecessary codes
The program should be clean and understandable

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)